## Slide 1: Cigre Paris
27-31 August 2018
Palais de Congrès

## Slide 2: Booth logistics
Sunday:
  Building up demo as of 2pm
  Access to the Opening Ceremony on Sunday from 4pm & cocktail afterwards
Monday:
  61850 meeting at 4pm, open for all, snacks and wine
  Show is open until 8pm
  Cocktail open to all in the Exhibition Halls on the 3 levels, from 6 pm to 8 pm
Friday: tear down booth as of 4pm

## Slide 3: Security
Security ordered:
Sun 26/08 19.00-8.00
Mon. 27/08 18.30-8.00
Tue. 28/08 18.30-8.00
Wed. 28/08 18.30-8.00
Thu. 29/08 18.30-8.00

## Slide 4: Actionlist – done!
LCD screen rental 24”– ordered
  Doble,Sisco, RTDS, SEL
Badges for the event – Done
Order CAT 6 cables copper and extender - Done
    Status delivery?
Content USB sticks (all-in): USB sticks ordered: 3.0 – 16GB

## Slide 5: Actionlist
Action items, to be done this week!
Slide running presentation (Platinum 3, Gold and Silver 2 slides)
    Missing: Schneider, Keri, Opal-RT, Sisco
UCA Banner for long wall
Update Demo Flyer
Presentation Schedule Poster, approval final schedule
Upload booth presentations to the site
UCAIug Cigre Pressrelease > Press center: finalize pressrelease
Prepare announcement 61850 booth meeting:
  Press center and/or mailing delegate list??

## Slide 6: Signage banner
UCAIug banner

## Slide 7: Signage
Presentation
schedule
Presentation
schedule

## Slide 8: Booth presentations Monday
Time | no | Assigned to | 
14.10-14.30 | 1 | UCAIug presentation, Margaret | 
14:30-14:50 | 2 | PCI – ERCOT’s nodal market solution | 
14:50-15:10 | 3 | SISCO: Data Management Using CIM and IEC 61850 | 
15:10-15:30 | 4 | TMW: Testing protocol gateways, HMIs, and SCADA in a simulated IEC 61850 system | 
15:30-15:50 | 5 | DNV GL PRP/HSR conformance and functional testing on Ethernet switches and IEDs (Bas Mulder) | 
15:50-16:10 | 6 | RTDS IEC 61850 representation of switchgear, switch controller, and interlocking functions for real-time simulations; | 
16:10-18.00 |  | UCA 61850 User’s Group Meeting Chair: Bas Mulder | 

## Slide 9: Booth presentations Tuesday
Time | No | Assigned to
12.00-12.30 | 7 | Doble: “Secure and Efficient Testing of IEC 61850-Based Protection and Control Systems” (30 min presentation)
12:20-12:40 | 8 | RTDS: Integrated testing for IEC 61850 compatible IEDs in a simulated smart automation system
12:40-13:00 | 9 | PCI- T-nexus AEP’s Network Model Management Solution
13:00-13:20 | 10 | SEL: 10X: Power System Technology 10 Years Ahead of Industry - International Standards Based Communications
13:20-13:40 | 11 | TMW Testing protocol gateways, HMIs, and SCADA in a simulated IEC 61850 system
13:40-14:00 | 12 | SISCO: Challenges and Solutions for GOOSE Traffic Monitoring
14:00-14:20 | 13 | RTDS IEC 61850 representation of switchgear, switch controller, and interlocking functions for real-time simulations;

## Slide 10: Booth presentations Wednesday
Time | Slot No | Assigned to
12.00 – 12.20 | 14 | DNV GL IEC 61850 utility profile testing (Bas Mulder)
12:20 – 12:40 | 15 | TMW: Practical use of Edition 2 testing features in live IEC 61850 systems
12:40 – 13:00 | 16 | SEL: Wide Area Synchronized Goose Message Analog Data Acquisition Creates Previously Impossible Solutions
13:00 – 13:20 | 17 | SISCO: Applying IEC 61850 to Distributed Energy Resources (DER)
13:20 – 13:40 | 18 | Schneider Electric ‘Process bus in Breaker and a half solutions’ - Tutorial
13:40 – 14:00 | 19 | Schneider Electric ‘IEC 61869 process bus – What are the key differences –
14:00 – 14:20 | 20 | SEL: 10X: Power System Technology 10 Years Ahead of Industry - Cyber Risk and Threat Defenses

## Slide 11: Booth presentations Thursday
Time | Slot No | Assigned to
12:00 – 12:20 | 21 | SEL: possible customer presentation
12:20 – 12:50 | 22 | Doble:“Secure and Efficient Testing of IEC 61850-Based Protection and Control Systems” (30 min presentation)
12:40– 13:00 | 23 | SISCO: Challenges and Solutions for GOOSE Traffic Monitoring
13:00 – 13:20 | 24 | Schneider Electric Unified IED modeling using IEC 61850 Flexible Product Naming
13:20 – 13:40 | 25 | Schneider Electric ‘IEC 61869 process bus – What are the key differences –
13:40– 14:00 | 26 | SEL: Award Winning Microgrid Controller Uses GOOSE Messages to Balance Utility Ties and Intermittent Renewables

## Slide 12: Any other business
Shipping your collateral: http://www.cigre-exhibition.com/wp-content/uploads/sites/1/Transport-Customs-Handling2.pdf
Booth hand-over: Sun. 26th August, 2pm
Dismantling booth: Fri. 31st August, 4pm